## TS_20418_11Q2_GC
PROPERTY | VALUE
WORK_ITEM_TEMPLATE_NAME | HW CO Develop and verify HW delivery (with layout)
PARENT_TYPE | Change Request
PARENT_SUMMARY | HW CO Develop and verify HW delivery (with layout)
PARENT_DESCRIPTION
CHILDREN1_TYPE | Issue
CHILDREN1_SUMMARY | HW1xx: Specify HW requirements
CHILDREN1_DESCRIPTION | Purpose: • To specify HW requirements derived from the system requirement specification and system design specification. • To verify HW requirements against the system design specification. • To detail the HW-SW interface (HSI) specification. Description:Technical system requirements are allocated to HW and SW. The requirements that are allocated to both are further partitioned to yield HW only requirements. The HW requirements are further detailed, considering design constraints and the impact of these design constraints on the HW.
CHILDREN2_TYPE | Issue
CHILDREN2_SUMMARY | HW2xx: Design HW
CHILDREN2_DESCRIPTION | Purpose: • To design the HW in accordance with the system design specification and the HW requirements. • To verify the HW design against the system design specification and the HW requirements Description: • HW design includes HW architectural design and HW detailed design. HW architectural design represents all HW components and their interactions with one another. HW detailed design is at the level of electrical schematics representing the interconnections between HW parts composing the HW components. • ASIL A, B, C, D specific: In order to develop a single HW design both HW safety requirements as well as all non-safety requirements have to be complied with. Hence, in this subphase, safety and non-safety requirements are handled within one development process.
CHILDREN_OF_CHILDREN1_TYPE_1 | Task
CHILDREN_OF_CHILDREN1_SUMMARY_1 | HW110: Specify HW (safety) requirements (HRS) & refine HW / SW Interface specification (HSI)
CHILDREN_OF_CHILDREN1_DESCRIPTION_1 | Activity Description: A) Specify HW (safety) requirements (HRS): • The HW requirements specification shall be derived from the system requirements allocated to HW. • The HW requirements shall be specified in accordance with PE. • The criteria for HW design verification shall be specified, including environmental conditions (temperature, vibration, EMI, etc.), specific operational environment (supply voltage, mission profile, etc.) and component specific requirements. • ASIL A, B, C, D specific: The HW safety requirements shall comply with the fault tolerant time interval for safety mechanisms and with the multiple-point fault detection interval. • ASIL (B), C, D specific: Target values for the HW architectural metrics and safety goal violations due to random HW failures shall be considered. B) Refine HW/SW interface specification • The HSI specification shall be refined sufficiently to allow for the correct control and usage of the HW by the SW, and shall describe each dependency between HW and SW. • The persons responsible for HW and SW development shall be jointly responsible for the verification of the adequacy of the refined HSI specification.
CHILDREN_OF_CHILDREN1_TYPE_2 | Review
CHILDREN_OF_CHILDREN1_SUMMARY_2 | HW130: Verify HW (safety) requirements (review HRS)
CHILDREN_OF_CHILDREN1_DESCRIPTION_2 | Activity Description: The HW requirements shall be verified in order to provide evidence of their consistency with the System, HW and SW specifications and requirements and their correctness and accuracy.
CHILDREN_OF_CHILDREN2_TYPE_1 | Task
CHILDREN_OF_CHILDREN2_SUMMARY_1 | HW212: Update worst case calculation & component capability evaluation (HW checklist)
CHILDREN_OF_CHILDREN2_DESCRIPTION_1 | Activity as subpart from Specify HW design (including HW architecture and detailed design).
CHILDREN_OF_CHILDREN2_TYPE_2 | Task
CHILDREN_OF_CHILDREN2_SUMMARY_2 | HW240: Perform HW (safety) analysis (FMEA / FMEDA) (ASIL (B),C,D)
CHILDREN_OF_CHILDREN2_DESCRIPTION_2 | Activity Description: • In general, the HW design shall be analyzed with the FMEA method • ASIL A, B, C, D specific: Safety Analyses on HW design to identify the causes of failures and the effects of faults shall be applied in accordance with Table 2 and ISO 26262-9:2011, Clause 8. • ASIL A, B, C, D specific: If applicable, evidence that the HW design is compliant with its requirements on independence shall be provided based on an analysis of dependent failures. • ASIL A, B, C, D specific: If new hazards introduced by the HW design are not already covered by an existing safety goal, they shall be introduced and evaluated in the hazard analysis and risk assessment in accordance with the change management process. • ASIL A, B, C, D specific: For each safety-related HW component or part, the safety analyses shall identify the following for the safety goal under consideration: safe faults, single-point faults or residual faults and multiple-point faults (either perceived, detected or latent). • ASIL (B), C, D specific: Evidence of the effectiveness of safety mechanisms to avoid single-point faults shall be made available.
FILED_AGAINST | Category 1
PLANNED_FOR | iteration.test1
SUMMARY_VARIABLE_VALUE | default summary | No use for 11Q GC
DESCRIPTION_VARIABLE_VALUE | updated description | No use for 11Q GC
PARENT_SUMMARY_AFTER_CREATE | Release for automation testing UC 173420 default summary updated description: default summary | No use for 11Q GC
SUMMARY_VARIABLE | Summary | No use for 11Q GC
DESCRIPTION_VARIABLE | Description | No use for 11Q GC